## Overview
Coinzy Web — Project Timeline
Project start date | 2026-10-05
Planning basis | Parallel AI agents; screen tasks use screens/day; leftovers + QA bug backlog use hours. Bug ETA from docs/bug-tracker.html velocity.
Remaining agent workdays
Calendar weeks
Projected finish
Overall progress
Unscheduled tasks
Screens per agent per day | 2
Planned screens |  | Agent weeks | Progress | Start | Finish
Landing pages
Auth and login
Homepage
AI Identification
Expert evaluation
Global Catalogue
Marketplace
Collections
Feed
Settings
Payments (deferred)
Review and fixes
Blogs
Note | Sync 23 (28 Oct 2026): Critical path = ClickUp web bugs. Velocity 34 pts/day (13 fixed today). 63 open (147 pts) → calendar ETA 2026-11-02 (~5d); workday finish ~2026-11-04. Task 22 = E2E+bug backlog 40h. Deferred (not QA blockers): Payments 20; Premium JWT on task 5.
Note | Bug ETA assumes today’s burst holds. Half-pace (~17 pts/day) → ~2026-11-06. See docs/bug-tracker.html.
Agent lanes | 5
Forecast from (edit) | 2026-10-28
Completion dates | Set progress to 100% and record the actual finish in Detailed Timeline column N. Early finishes release dependent work; forecasts use only remaining work and agent availability.
Sort order | Detailed Timeline stays in task-ID order (dependency and agent-lane formulas read earlier rows by position, so sorting it would break the schedule). Weekly View is listed by progress (highest first), then task ID, matching the HTML timeline.
Leftover hours (sum)
Hours per agent day | 8
Leftovers (hours)

## Detailed Timeline
ID | Section | Work package / deliverable | Remaining workdays | Start date | Finish date | Progress (edit) | Status | Start week | Finish week | Depends on ID (edit) | Screens (edit) | Agent lane | Recorded completion (edit) | Original workdays | Agent busy through | Hours (edit)
1 | Landing pages | Main landing page: Main page, shared header/footer and navigation; done with real coin images and favicon |  |  |  | 100% |  |  |  | 0 | 2 | A | 2026-10-05
2 | Landing pages | Feature landing pages: Done. Expert CTAs peeled → leftover task 24 (1h). |  |  |  | 100% |  |  |  | 1 | 6 | A | 2026-10-09
3 | Auth and login | Account access: Done: welcome, email signup/login, guest sessions, forgot/reset APIs, OTP and new-password flow, Figma error states (1758:124172), Trackzio Terms/Privacy links, HTTP-only cookies, signed-in redirects and single-history auth steps; logged-out CTAs use /auth?next= (908/905 auth modals out of scope); Google sign-in disabled on web |  |  |  | 100% |  |  |  | 2 | 8 | A | 2026-10-06
4 | Homepage | Free user dashboard: Done: signed-in /home (Figma 1898:205770) with live marketplace rows, Coin of the Day (free drawer and Premium upsell modal) and a 3-item Global Catalogue widget |  |  |  | 100% |  |  |  | 0 | 4 | B | 2026-10-06
5 | Homepage | Premium experience: ~95% test multi-plan purchase (coinzy_premium cookie). JWT + Payments 20 deferred/unscheduled (not QA blocker). |  |  |  | 95% |  |  |  | 4 |  | B
6 | AI Identification | Start identification: Done: /identify upload (1828:206837), flip-coin (1828:206843), camera + zoom (1828:206846), blocked camera (1828:206844), analyse (1828:206840), failure / not-found (2098:158944), free plan card (1828:206842), error toasts (1493:236892), POST /api/ai/identify-v2; dev black-image debug to force failure |  |  |  | 100% |  |  |  | 0 | 8 | C | 2026-10-06
7 | AI Identification | Results and actions: Done: matches, result details, collection add, rate-match rail (Figma Solid selected; dummy Feedback sent). |  |  |  | 100% |  |  |  | 6 | 8 | C | 2026-10-09
8 | Expert evaluation | New request: Done (hub/upload/submit + staff dummy pay). Public credits → Payments 20; landing CTAs → leftover 24. |  |  |  | 100% |  |  |  | 7 | 6 | C | 2026-10-09
9 | Expert evaluation | Existing requests: Done — list, poll+retry, report+feedback, Socket.IO user-room (REST refresh on events). |  |  |  | 100% |  |  |  | 8 | 8 | C | 2026-10-09
10 | Global Catalogue | Browse catalogue: Done: live API coin grid, category filters, pagination and name search (?q=, composes with category filters; the API matches whole coin names only; search UI is not in Figma, built on the dashboard search pill) |  |  |  | 100% |  |  |  | 0 | 6 | D | 2026-10-06
11 | Global Catalogue | Coin details: Done: live API details, grades, tabs; free vs Premium tab gating (1348:137792 / 1341:249499); signed-in app shell; wishlist hearts via PUT/DELETE archetypes/wishlist (grid + details) |  |  |  | 100% |  |  |  | 10 | 4 | D | 2026-10-06
12 | Marketplace | Browse listings: Done: logged-out landing (793:77834) and category pages (793:77612) with live rows, pagination and title search (?q=, case-insensitive whole words; search UI is not in Figma, built on the dashboard search pill); signed-in /marketplace (1356:154252) with filterItems filters and fetchAll; /home marketplace chips and search; logged-out List a coin → /auth?next= |  |  |  | 100% |  |  |  | 11 | 6 | D | 2026-10-06
13 | Marketplace | Listing details: Done: live listing, seller details; signed-in Contact seller modal (1356:164759); logged-out redacted contact + /auth?next= (no auth modal) |  |  |  | 100% |  |  |  | 12 | 4 | D | 2026-10-05
14 | Marketplace | Create listings: Done — List a coin, From Owned, seller profile, Add for Sale, self listing with Remove + Mark as sold (PATCH /marketplace/markSold/:id) |  |  |  | 100% |  |  |  | 13 | 8 | D | 2026-10-09
15 | Collections | Browse collections: Done — home, bucket/private grids, filters, empty state, coin details; shared catalogue Pagination on grids |  |  |  | 100% |  |  |  | 7 | 6 | E | 2026-10-09
16 | Collections | Manage collection: Done. Edit/rename + leftover 27 cancelled (out of scope). |  |  |  | 100% |  |  |  | 15 | 6 | E | 2026-10-09
17 | Feed | Community feed: Done: /feed (Figma Copy 951:87324) — composer, post cards (like/bookmark/⋯ edit·delete), create/edit modal (title+content, max 2 images, Discussion/Buy-Sell), delete confirm, toast; Firebase all-posts + Storage posts/{id}/images (Android PostRepository parity) |  |  |  | 100% |  |  |  | 5 | 6 | B | 2026-10-09
18 | Feed | Personal activity: Done: Saved posts + My posts rail; comments/replies modal; inline Notification rail; report; Firestore comments/likes/bookmarks/notifications same paths as Android |  |  |  | 100% |  |  |  | 17 | 4 | B | 2026-10-09
19 | Settings | Account settings: Done. Billing entry peeled → leftover task 28 (1h); checkout → Payments 20. |  |  |  | 100% |  |  |  | 18 | 6 | B | 2026-10-09
20 | Payments (deferred) | Payments DEFERRED: Experts web credits + Premium checkout + Plan & billing. |  |  |  | 0% |  |  |  | 3 |  | A
21 | Payments (deferred) | Folded into task 20 — deferred payments (unscheduled). |  |  |  | 0% |  |  |  | 20 |  | A
22 | Review and fixes | E2E QA + ClickUp bug backlog: 13 fixed / 34 pts on 2026-10-28; 63 open / 147 pts → ~5 agent days (40h) at 34 pts/day. british-coins empty chip + other-apps Coming soon intentional. |  |  |  | 0% |  |  |  | 0 |  | QA |  |  |  | 40
23 | Blogs | Blog experience: Done: six articles, category filtering and load more; duration unscheduled |  |  |  | 100% |  |  |  | Parallel |  |  | 2026-10-05
24 | Leftovers (hours) | Landing Expert CTAs: Done — Get Expert’s opinion? / View all → /auth?next=/experts |  |  |  | 1 |  |  |  | 2 |  | A | 2026-10-09 |  |  | 1
25 | Leftovers (hours) | Identify rate-match: Done — Figma rate card (Stroke + Solid primary selected) + Message/Submit; dummy Feedback sent toast (no API). |  |  |  | 1 |  |  |  | 7 |  | C | 2026-10-14 |  |  | 3
26 | Leftovers (hours) | Experts Socket.IO: Done — socket.io-client → Experts host auth.userId; events trigger REST refresh / router.refresh. Poll kept as fallback. |  |  |  | 1 |  |  |  | 9 |  | C | 2026-10-14 |  |  | 8
27 | Leftovers (hours) | (cancelled — was manage polish): Out of scope. Edit/rename private not on web. ID kept. |  |  |  | 1 |  |  |  | 0 |  | E | 2026-10-09
28 | Leftovers (hours) | Settings billing entry: Done — opens test Premium plans. Real gateway → Payments 20. |  |  |  | 1 |  |  |  | 19 |  | B | 2026-10-14 |  |  | 1
Formulas:
Start date = IF([Progress (edit)]>=1,IF([Recorded completion (edit)]="",Overview!$B27,[Recorded completion (edit)]),IF([Remaining workdays]="","",IF(IF([Depends on ID (edit)]=0,FALSE(),INDEX(F2:F29,[Depends on ID (edit)])=""),"",WORKDAY(MAX(Overview!$B2-1,Overview!$B27-1,IF([Depends on ID (edit)]=0,0,INDEX(F2:F29,[Depends on ID (edit)])),0),1))))
Start date = IF([Progress (edit)]>=1,IF([Recorded completion (edit)]="",Overview!$B27,[Recorded completion (edit)]),IF([Remaining workdays]="","",IF(IF([Depends on ID (edit)]=0,FALSE(),INDEX(F2:F29,[Depends on ID (edit)])=""),"",WORKDAY(MAX(Overview!$B2-1,Overview!$B27-1,IF([Depends on ID (edit)]=0,0,INDEX(F2:F29,[Depends on ID (edit)])),IFERROR(LOOKUP(2,1/(M2:[Agent lane, row above]=[Agent lane]),P2:[Agent busy through, row above]),0)),1))))
Finish date = IF([Progress (edit)]>=1,[Start date],IF([Start date]="","",WORKDAY([Start date],[Remaining workdays]-1)))

## Weekly View
ID | Section | Work package | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26